## Sheet1
Schedule Management
Project Name: Health and Wellness App Development | Date: 08/23/2020
Work Breakdown Structure Categories
1. Initiating | Start Date | End Date | Responsible | Estimated Hours per person | [5 empty] | Total
2. Planning | 2020-08-23 | 2020-08-24 |  | Annie | Sindhuja | Alekhya | Tarun | Vigneshwar | Neelesh | Est. Hours
3. Designing | 2020-08-24 | 11/31/2020 | Team | 1 | 1 | 1 |  | 2 |  | 5
3.1 UI Design | 2020-08-25 | 2020-09-15 | Sindhuja |  | 6 |  |  |  |  | 6
3.2 Synthesis of Design | 2020-09-16 | 2020-10-15 | Team | 2 |  | 2 | 1.5 | 2 | 0.5 | 8
3.3 Implementation Iteration | 2020-10-16 | 2020-11-04 | Vigneshwar |  |  |  |  | 4.5 |  | 4.5
3.4 Early release and Contract finalization | 2020-11-05 | 11/31/2020 | Alekhya |  |  | 5 |  |  |  | 5
4. Implementation | 2020-01-20 | 2020-03-28 | Team | 3 | 1.5 | 1.5 | 1.5 | 1 | 2 | 10.5
4.1 Application Development | 2020-01-20 | 2020-02-05 | Team | 1.5 | 2 | 1 | 1 |  | 1.5 | 7
4.2 PWA Implementation | 2020-02-06 | 2020-02-28 | Annie | 3 | [5 empty] | 3
4.3 Android/iOS Implementation | 2020-03-01 | 2020-03-30 | Tarun |  |  |  | 4.5 | 0.5 |  | 5
5. Monitoring and Controlling | 2020-04-03 | 2020-04-17 | Team | 1 | 1.5 | 1 | 2 |  | 1 | 6.5
6. Closing | 2020-04-18 | 2020-05-01 | Neelesh | [5 empty] | 5 | 5
|  |  | Total | 11.5 | 12 | 11.5 | 10.5 | 10 | 5 | 60.5